## Oct
Week | Team Member | Tasks completed this week | Status | Useful information and links(Simple summary) | Planned tasks for next week
Week 1(Oct 12th - Oct 18th) | AQSA-AHMED | Assisted in organizing initial fraud case records; began drafting notes for documentation. | Completed | Collected alerts from official sources. | Continue dataset documentation; support report drafting.
| LIN Yueying | Began collecting academic references on fraud detection; supported dataset categorization. | Completed | Initial sources gathered for literature review. | Expand literature review; refine dataset categories.
| TAN James Anthroi | Assigned tasks to team members; edited and refined FYP document report (structure, formatting, references). Explored Fraud-R1 GitHub repo; began reading about RAG concepts. | Completed | Updated report sections with fraud case collection and simulator design; coordinated team progress. https://github.com/kaustpradalab/Fraud-R1 | Continue editing methodology/results; integrate supervisor feedback; oversee team execution; deepen RAG study.
| TAN Xiuhao | 1. Collect more official fraud cases. 2. Learn Fraud - R1's LLM method for generating fraud cases. 3. Build a demo version of the AI ​​fraud simulator to test the basic LLM fraud generation capabilities. 4. Understand the basic principles of RAG. | Completed | Used sample fraud cases to check simulator functionality. https://www.adcc.gov.hk/zh-cn/alerts.html | 1. Learn RAG combined with LLM techniques. 2. Stay tuned for official datasets.
Week 2(Oct 19th - Oct 25th) | AQSA-AHMED | Supported dataset documentation; maintained records of fraud case sources. | Completed | Draft notes compiled for reporting. | Continue documentation; assist in methodology write‑up.
| LIN Yueying | Expanded literature search; organized fraud datasets by category. | Completed | Sources collected for fraud detection methods. | Draft literature review notes; refine dataset categorization.
| TAN James Anthroi | Finalized methodology draft; integrated supervisor feedback; compiled resources; coordinated team progress. | Completed | Strengthened methodology with academic references. | Begin editing discussion framework; prepare mid‑sprint summary.
| TAN Xiuhao | Compiled fraud datasets from GitHub/Kaggle for study. | Completed | https://www.kaggle.com/datasets/shivamb/real-or-fake-fake-jobposting-prediction/data https://www.kaggle.com/datasets/srisaisuhassanisetty/fake-job-postings | Continue dataset exploration; align with backend detection workflow.
Week 3(Oct 26th - Nov 1st) | AQSA-AHMED | Summarized fraud case dataset; highlighted patterns for detection analysis. | Completed | Dataset categorized by fraud type. | Continue dataset refinement for reporting.
| LIN Yueying | Drafted research notes on fraud detection approaches; collected academic references. | Completed | Collected academic sources on RAG + LLM use cases. | Expand literature review; integrate into report.
| TAN James Anthroi | Edited draft sections; compiled team’s Week 2 outputs into documentation. | Completed | Consolidated team contributions into report. | Draft discussion/conclusion framework.
| TAN Xiuhao | Continued learning phase: explored fraud datasets and preprocessing techniques. | Completed | Notes compiled on Kaggle datasets and official fraud alerts. | Deepen understanding of backend workflows; assist in dataset preparation.
Week 4(Nov 2nd - Nov 8th) | AQSA-AHMED | Refined fraud dataset summaries; prepared draft tables for report inclusion. | Completed | Dataset tables categorized by fraud type. | Assist in integrating dataset tables into methodology draft.
| LIN Yueying | Expanded literature review; synthesized academic references on fraud detection. | Completed | Added scholarly sources. | Begin drafting literature review section in FYP report.
| TAN James Anthroi | Drafted discussion framework; ensured examiner alignment; coordinated mid‑sprint summary. | Completed | Mid‑sprint summary compiled with methodology draft. | Refine discussion/conclusion; integrate supervisor feedback.
| TAN Xiuhao | Explored fraud datasets (Kaggle, official alerts); validated preprocessing pipeline for detection tasks. | In progress | Fraud datasets cleaned and structured for analysis. | Continue dataset refinement; align with backend detection framework.
Week 5(Nov 9th - Nov 15th) | AQSA-AHMED | Integrated dataset refinements into draft sections; highlighted anomalies and fraud patterns. | In progress | Fraud anomalies flagged for study. | Continue anomaly analysis; prepare contribution to draft discussion.
| LIN Yueying | Drafted literature review section; linked fraud detection concepts to academic use cases. | Completed | Literature review section ready for supervisor review. | Revise literature review based on feedback; assist in discussion drafting.
| TAN James Anthroi | Refined discussion draft; edited report for coherence; ensured examiner‑ready formatting. | Completed | Report aligned with APA style and examiner expectations. | Finalize conclusion draft; oversee integration of all sections.
| TAN Xiuhao | Enhanced dataset exploration; improved preprocessing pipeline for fraud detection tasks. | In progress | Fraud detection pipeline outputs more consistent results. | Continue refinement; document backend workflow notes.
Week 6(Nov 16th - Nov 22nd) | AQSA-AHMED | Completed dataset anomaly analysis; contributed findings to draft sections. | Completed | Draft updated with anomaly insights. | Assist in preparing final sprint summary.
| LIN Yueying | Revised literature review; integrated supervisor feedback; polished citations. | Completed | Literature review finalized with APA references. | Support conclusion drafting; prepare oral presentation notes.
| TAN James Anthroi | Finalized conclusion draft; coordinated sprint backlog consolidation. | Completed | Report examiner‑ready with methodology, literature review, and discussion drafts. | Prepare final sprint presentation; oversee submission readiness.
| TAN Xiuhao | Continued studying fraud detection datasets; explored preprocessing techniques and RAG concepts. | Completed | Notes compiled on dataset structures and RAG learning resources. | Deepen understanding of RAG integration; assist in preparing learning notes for team.

## Nov
Week | Team Member | Tasks completed this week | Status | Useful information and links(Simple summary) | Planned tasks for next week
Week 4(Nov 2nd - Nov 8th) | AQSA-AHMED | Refined fraud dataset summaries; prepared draft tables for report inclusion. | Completed | Dataset tables categorized by fraud type. | Assist in integrating dataset tables into methodology draft.
| LIN Yueying | Expanded literature review; synthesized academic references on fraud detection. | Completed | Added scholarly sources. | Begin drafting literature review section in FYP report.
| TAN James Anthroi | Drafted discussion framework; ensured examiner alignment; coordinated mid‑sprint summary. | Completed | Mid‑sprint summary compiled with methodology draft. | Refine discussion/conclusion; integrate supervisor feedback.
| TAN Xiuhao | Explored fraud datasets (Kaggle, official alerts); validated preprocessing pipeline for detection tasks. | Completed | Fraud datasets cleaned and structured for analysis. | Continue dataset refinement; align with backend detection framework.
Week 5(Nov 9th - Nov 15th) | AQSA-AHMED | Integrated dataset refinements into draft sections; highlighted anomalies and fraud patterns. | Completed | Fraud anomalies flagged for study. | Continue anomaly analysis; prepare contribution to draft discussion.
| LIN Yueying | Drafted literature review section; linked fraud detection concepts to academic use cases. | Completed | Literature review section ready for supervisor review. | Revise literature review based on feedback; assist in discussion drafting.
| TAN James Anthroi | Refined discussion draft; edited report for coherence; ensured examiner‑ready formatting. | Completed | Report aligned with APA style and examiner expectations. | Finalize conclusion draft; oversee integration of all sections.
| TAN Xiuhao | Enhanced dataset exploration; improved preprocessing pipeline for fraud detection tasks. | Completed | Fraud detection pipeline outputs more consistent results. | Continue refinement; document backend workflow notes.
Week 6(Nov 16th - Nov 22nd) | AQSA-AHMED | Completed dataset anomaly analysis; contributed findings to draft sections. | Completed | Draft updated with anomaly insights. | Assist in preparing final sprint summary.
| LIN Yueying | Revised literature review; integrated supervisor feedback; polished citations. | Completed | Literature review finalized with APA references. | Support conclusion drafting; prepare oral presentation notes.
| TAN James Anthroi | Finalized conclusion draft; coordinated sprint backlog consolidation. | Completed | Report examiner‑ready with methodology, literature review, and discussion drafts. | Prepare final sprint presentation; oversee submission readiness.
| TAN Xiuhao | Continued studying fraud detection datasets; explored preprocessing techniques and RAG concepts. | Completed | Notes compiled on dataset structures and RAG learning resources. | Deepen understanding of RAG integration; assist in preparing learning notes for team.

## Task
Member | Task | Status
AQSA-AHMED |  | TRUE
LIN Yueying |  | TRUE
TAN James Anthroi |  | TRUE
TAN Xiuhao |  | TRUE