## Oct
Week | Team Member | Tasks completed this week | Status | Useful information and links(Simple summary) | Planned tasks for next week
Week 1(Oct 12th - Oct 18th) | AQSA-AHMED
LIN Yueying
| TAN James Anthroi | Assigned tasks to team members; edited and refined FYP document report (structure, formatting, references). Explored Fraud-R1 GitHub repo; began reading about RAG concepts. | In progress | Updated report sections with fraud case collection and simulator design; coordinated team progress. https://github.com/kaustpradalab/Fraud-R1 | Continue editing methodology and results sections; integrate supervisor feedback; oversee task execution. Continue studying RAG basics.
| TAN Xiuhao | 1. Collect more official fraud cases. 2. Learn Fraud - R1's LLM method for generating fraud cases. 3. Build a demo version of the AI ​​fraud simulator to test the basic LLM fraud generation capabilities. 4. Understand the basic principles of RAG. | Completed | Used sample fraud cases to check simulator functionality. https://www.adcc.gov.hk/zh-cn/alerts.html | 1. Learn RAG combined with LLM techniques. 2. Stay tuned for official datasets.
Week 2(Oct 19th - Oct 25th) | AQSA-AHMED
LIN Yueying
| TAN James Anthroi | Finalized methodology section in FYP report; integrated supervisor feedback; coordinated team progress. |  |  | Continue editing results and discussion sections; prepare mid-sprint progress summary.
| TAN Xiuhao |  |  | https://www.kaggle.com/datasets/shivamb/real-or-fake-fake-jobposting-prediction/data https://www.kaggle.com/datasets/srisaisuhassanisetty/fake-job-postings
Week 3(Oct 26th - Nov 1th) | AQSA-AHMED | Summarized fraud case dataset; highlighted patterns for simulator training. |  | Dataset now categorized by type of fraud.
| LIN Yueying | Drafted research notes on RAG applications in fraud detection. |  | Collected references on RAG + LLM use cases.
| TAN James Anthroi | Edited results section of FYP report; compiled team’s Week 2 outputs into documentation. |  | Updated report with dataset structure and simulator improvements. | Draft discussion and conclusion sections; prepare slides for progress presentation.
TAN Xiuhao

## Task
Member | Task | Status
AQSA-AHMED | Organized collected fraud cases into structured dataset for simulator testing. | FALSE
LIN Yueying | Notes from Fraud-R1 repo and online resources. | FALSE
TAN James Anthroi |  | FALSE
TAN Xiuhao |  | FALSE